## Summary
STEP 1
Project ABC - Sprint Summary
Sprint No # | PI 2- Sprint 5
Sprint Duration | 2
Sprint Goal | "Check-In" to stock market App with proper Authorization & security
Sprint From | 2021-04-19
Sprint To | 2021-04-30
Total working Days | 9
STEP 2
Holiday Calendar
|  | New Year's Day | 2021-01-01
|  | Good Friday | 2021-04-02
|  | Easter Monday | 2021-04-05
|  | King's Day | 2021-04-27
|  | Ascension Day | 2021-05-13
|  | Whit Monday | 2021-05-24

## Sprint Capacity
| STEP 3 |  | Leave ( days) | STEP 4 |  | STEP 5 | STEP 6 | STEP 6 |  |  | Events | Hrs
S No | Team Member | Hours/Day |  | Allocation % | Available efforts ( in Hrs) | Events Time( Hrs) | Plan Leave (Hrs) | Team Members( Hrs) | Net Work Hours |  | Sprint Planning | 1
1 | James | 8 |  | 100 | 72 | 63.75 | 8 | 5 | 50.75 | 6.3438 | Retrospective | 1
2 | Kiran | 8 |  | 100 | 72 | 72 | 0 | 2 | 70 | 8.75 | Sprint Review | 2
3 | Sander | 8 |  | 100 | 72 | 72 | 0 | 2 | 70 | 8.75 | Refinement | 2
4 | Stephen | 8 |  | 100 | 72 | 72 | 0 | 3 | 69 | 8.625
5 | Anil | 8 |  | 100 | 72 | 72 | 0 | 3 | 69 | 8.625
6 | Sally | 8 |  | 100 | 72 | 72 | 0 |  | 72 | 9 | Daily Standup | 2.25
7 | Jerin | 8 |  | 100 | 72 | 72 | 0 |  | 72 | 9
8 | Liz | 8 |  | 100 | 72 | 72 | 0 |  | 72 | 9 | Total | 8.25 | Hrs
[5 empty] | 576 | 567.75 | 8 |  | 544.75 | 68.0938
1SP = 8 hr
[9 empty] | James | US1 | 5
[9 empty] | Kiran | US2 | 3
[9 empty] | Sander | US3 | 2, 5
[9 empty] | Stephen | US4 | 8
[9 empty] | Anil | US5 | 8
[9 empty] | Sally | US6 | 5
[9 empty] | Jerin | US7 | 5
[9 empty] | Liz | US8 | 8